## Summary
AIRPAY ACADEMY — Production Import Upgrade Log
Date: April 2026 ¦ Source: airpayprod 6th April backup → Local XAMPP Moodle 4.5.10
Status | Count | Description
To be upgraded | 53 | Existing plugins updated from 4.1 to 4.5
To be installed | 30 | New plugins in Moodle 4.5 (not in production 4.1)
To be deleted | 21 | Legacy plugins removed in Moodle 4.5
Missing from disk! | 1 | Plugin in DB but not on disk — needs attention
Category | Count
Activity modules | 25
Legacy (deleted) | 16
Blocks | 7
Question types | 7
TinyMCE plugins | 5
Admin tools | 5
MFA Factors | 5
Enrolment | 4
Authentication | 4
Local plugins | 4
Text filters | 3
Editors | 3
Themes | 3
AI Placements | 2
AI Providers | 2
Communication | 2
Certificate elements | 2
H5P frameworks | 2
Reports | 1
Custom fields | 1
SMS gateways | 1
Payment gateways | 1
Custom Airpay plugins being installed:
Airpay Compliance Dashboard | /blocks/airpay_compliance | 2026040500
Epsilon (airpayux) | /theme/airpayux | 2026040500
Airpay Integrations Hub | /local/airpay_integrations | 2026040500
Airpay Employee Lifecycle | /local/airpay_lifecycle | 2026040500
Airpay Pages | /local/airpay_pages | 2026040400

## All Plugins
Category | Plugin Name | Directory | Current Version | New Version | Source | Status
Activity modules | Assignment | /mod/assign | 2022112801 | 2024100700 | Standard | To be upgraded
Activity modules | BigBlueButton | /mod/bigbluebuttonbn | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Book | /mod/book | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Chat | /mod/chat | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Choice | /mod/choice | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Database | /mod/data | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Feedback | /mod/feedback | 2022112800 | 2024100701 | Standard | To be upgraded
Activity modules | Folder | /mod/folder | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Forum | /mod/forum | 2022112801 | 2024100700 | Standard | To be upgraded
Activity modules | Glossary | /mod/glossary | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | H5P | /mod/h5pactivity | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | IMS content package | /mod/imscp | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Text and media area | /mod/label | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Lesson | /mod/lesson | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | External tool | /mod/lti | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Page | /mod/page | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Quiz | /mod/quiz | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | File | /mod/resource | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | SCORM package | /mod/scorm | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Subsection | /mod/subsection |  | 2024100700 | Standard | To be installed
Activity modules | Survey | /mod/survey | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | URL | /mod/url | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Wiki | /mod/wiki | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | Workshop | /mod/workshop | 2022112800 | 2024100700 | Standard | To be upgraded
Activity modules | assignment (legacy) |  | 2022112800 |  | Standard | To be deleted
Blocks | Accessibility review | /blocks/accessreview | 2022112800 | 2024100700 | Standard | To be upgraded
Blocks | Activities | /blocks/activity_modules | 2022112800 | 2024100700 | Standard | To be upgraded
Blocks | Airpay Compliance Dashboard | /blocks/airpay_compliance |  | 2026040500 | Additional (Custom) | To be installed
Blocks | Calendar | /blocks/calendar_month | 2022112800 | 2024100700 | Standard | To be upgraded
Blocks | Course completion status | /blocks/completionstatus | 2022112800 | 2024100700 | Standard | To be upgraded
Blocks | Course overview | /blocks/myoverview | 2022112800 | 2024100700 | Standard | To be upgraded
Blocks | Timeline | /blocks/timeline | 2022112800 | 2024100700 | Standard | To be upgraded
Question types | Ordering | /question/type/ordering |  | 2024100700 | Standard | To be installed
Question types | Multiple choice | /question/type/multichoice | 2022112800 | 2024100700 | Standard | To be upgraded
Question types | Short answer | /question/type/shortanswer | 2022112800 | 2024100700 | Standard | To be upgraded
Question types | True/False | /question/type/truefalse | 2022112800 | 2024100700 | Standard | To be upgraded
Question types | Essay | /question/type/essay | 2022112800 | 2024100700 | Standard | To be upgraded
Question types | Calculated | /question/type/calculated | 2022112800 | 2024100700 | Standard | To be upgraded
Question types | Matching | /question/type/match | 2022112800 | 2024100700 | Standard | To be upgraded
Text filters | Code highlighter | /filter/codehighlighter |  | 2024100700 | Standard | To be installed
Text filters | MathJax | /filter/mathjaxloader | 2022112800 | 2024100700 | Standard | To be upgraded
Text filters | tidy (legacy) |  | 2022112800 |  | Standard | To be deleted
Editors | Atto HTML editor | /lib/editor/atto | 2022112800 | 2024100700 | Standard | To be upgraded
Editors | TinyMCE editor | /lib/editor/tiny | 2022112800 | 2024100701 | Standard | To be upgraded
Editors | tinymce (legacy) |  | 2022112800 |  | Standard | To be deleted
TinyMCE plugins | AI placement | /lib/editor/tiny/plugins/aiplacement |  | 2024100700 | Standard | To be installed
TinyMCE plugins | HTML | /lib/editor/tiny/plugins/html |  | 2024100700 | Standard | To be installed
TinyMCE plugins | Link | /lib/editor/tiny/plugins/link |  | 2024100700 | Standard | To be installed
TinyMCE plugins | No auto-link | /lib/editor/tiny/plugins/noautolink |  | 2024100700 | Standard | To be installed
TinyMCE plugins | TinyMCE Premium | /lib/editor/tiny/plugins/premium |  | 2024100700 | Standard | To be installed
Enrolment | Manual enrolments | /enrol/manual | 2022112800 | 2024100700 | Standard | To be upgraded
Enrolment | Self enrolment | /enrol/self | 2022112800 | 2024100700 | Standard | To be upgraded
Enrolment | Guest access | /enrol/guest | 2022112800 | 2024100700 | Standard | To be upgraded
Enrolment | Cohort sync | /enrol/cohort | 2022112800 | 2024100700 | Standard | To be upgraded
Authentication | Manual accounts | /auth/manual | 2022112800 | 2024100700 | Standard | To be upgraded
Authentication | Email self-registration | /auth/email | 2022112800 | 2024100700 | Standard | To be upgraded
Authentication | OAuth 2 | /auth/oauth2 | 2022112800 | 2024100700 | Standard | To be upgraded
Authentication | Web services | /auth/webservice | 2022112800 | 2024100700 | Standard | To be upgraded
Admin tools | Certificate manager | /admin/tool/certificate | 2021020800.5 | 2025031804 | Additional | To be upgraded
Admin tools | Multi-factor authentication | /admin/tool/mfa |  | 2024100700 | Standard | To be installed
Admin tools | TCPDF Fonts | /admin/tool/tcpdffonts | 2021090103 | 2025120101 | Additional | To be upgraded
Admin tools | Learning plans | /admin/tool/lp | 2022112800 | 2024100701 | Standard | To be upgraded
Admin tools | innodb (legacy) |  | 2022112800 |  | Standard | To be deleted
MFA Factors | Non-administrator | /admin/tool/mfa/factor/admin |  | 2024100700 | Standard | To be installed
MFA Factors | Email | /admin/tool/mfa/factor/email |  | 2024100700 | Standard | To be installed
MFA Factors | Authenticator app | /admin/tool/mfa/factor/totp |  | 2024100700 | Standard | To be installed
MFA Factors | Security key | /admin/tool/mfa/factor/webauthn |  | 2024100700 | Standard | To be installed
MFA Factors | SMS mobile phone | /admin/tool/mfa/factor/sms |  | 2024100702 | Standard | To be installed
AI Placements | Course assistance | /ai/placement/courseassist |  | 2024100700 | Standard | To be installed
AI Placements | Text editor | /ai/placement/editor |  | 2024100700 | Standard | To be installed
AI Providers | Azure AI API | /ai/provider/azureai |  | 2024100700 | Standard | To be installed
AI Providers | OpenAI API | /ai/provider/openai |  | 2024100700 | Standard | To be installed
Communication | Custom link | /communication/provider/customlink |  | 2024100700 | Standard | To be installed
Communication | Matrix | /communication/provider/matrix |  | 2024100700 | Standard | To be installed
Certificate elements | Dynamic fields | /admin/tool/certificate/element/program |  | 2025031804 | Additional | To be installed
Certificate elements | modulename (legacy) |  | 2017111300 |  | Additional | Missing from disk!
Reports | Theme usage | /report/themeusage |  | 2024100700 | Standard | To be installed
Custom fields | Number | /customfield/field/number |  | 2024100703 | Standard | To be installed
H5P frameworks | H5P framework v1.27 | /h5p/h5plib/v127 |  | 2024100700 | Standard | To be installed
H5P frameworks | v124 (legacy) |  | 2022112800 |  | Standard | To be deleted
Themes | Epsilon (airpayux) | /theme/airpayux |  | 2026040500 | Additional (Custom) | To be installed
Themes | Boost | /theme/boost | 2022112800 | 2024100700 | Standard | To be upgraded
Themes | Classic | /theme/classic | 2022112800 | 2024100700 | Standard | To be upgraded
Local plugins | Airpay Integrations Hub | /local/airpay_integrations |  | 2026040500 | Additional (Custom) | To be installed
Local plugins | Airpay Employee Lifecycle | /local/airpay_lifecycle |  | 2026040500 | Additional (Custom) | To be installed
Local plugins | Airpay Pages | /local/airpay_pages |  | 2026040400 | Additional (Custom) | To be installed
Local plugins | Course recompletion | /local/recompletion | 2023012600 | 2025041400 | Additional | To be upgraded
SMS gateways | AWS | /sms/gateway/aws |  | 2024100700 | Standard | To be installed
Payment gateways | PayPal | /payment/gateway/paypal | 2022112800 | 2024100700 | Standard | To be upgraded
Legacy (deleted) | memcached cache store |  | 2022112800 |  | Standard | To be deleted
Legacy (deleted) | mongodb cache store |  | 2022112801 |  | Standard | To be deleted
Legacy (deleted) | legacy log store |  | 2022112800 |  | Standard | To be deleted
Legacy (deleted) | assignment offline |  | 2022112800 |  | Additional | To be deleted
Legacy (deleted) | assignment online |  | 2022112800 |  | Additional | To be deleted
Legacy (deleted) | assignment upload |  | 2022112800 |  | Additional | To be deleted
Legacy (deleted) | assignment uploadsingle |  | 2022112800 |  | Additional | To be deleted
Legacy (deleted) | tinymce ctrlhelp |  | 2022112800 |  | Additional | To be deleted
Legacy (deleted) | tinymce managefiles |  | 2022112800 |  | Additional | To be deleted
Legacy (deleted) | tinymce moodleemoticon |  | 2022112800 |  | Additional | To be deleted
Legacy (deleted) | tinymce moodleimage |  | 2022112800 |  | Additional | To be deleted
Legacy (deleted) | tinymce moodlemedia |  | 2022112800 |  | Additional | To be deleted
Legacy (deleted) | tinymce moodlenolink |  | 2022112800 |  | Additional | To be deleted
Legacy (deleted) | tinymce pdw |  | 2022112800 |  | Additional | To be deleted
Legacy (deleted) | tinymce spellchecker |  | 2022112800 |  | Additional | To be deleted
Legacy (deleted) | tinymce wrap |  | 2022112800 |  | Additional | To be deleted